## Template
Action ID (Sequential) | Source Study (HAZOP / HAZID / SIL / LOPA / PHA / Incident / Audit) | Study Reference and Node | Study Date | Recommendation Text | Recommendation Type (Engineering / Procedural / Training / Inspection) | Discipline (Process / Mechanical / Instrumentation / Electrical / Civil / HSE) | Equipment / Tag Reference | P&ID Reference | Risk Category (Tolerable / ALARP / Intolerable) | Priority (Critical / High / Medium / Low) | Action Owner (Name + Organization) | Action Approver | Target Closeout Date | Revised Target Date (with Justification) | Closeout Evidence Reference (Document / Drawing / Photo) | Closeout Status (Open / In Progress / Closed / Rejected / Superseded) | Closeout Date | Verification By (Independent) | Verification Date | MOC Reference | Notes
Example value 1 for Action ID (Sequential) | Example value 1 for Source Study (HAZOP / HAZID / | REF-001 | 2024-09-15 | Example value 1 for Recommendation Text | Example value 1 for Recommendation Type (Engineeri | Mechanical (Pumps) | REF-001 | P&ID-001 Rev B | Example value 1 for Risk Category (Tolerable / ALA | High | EPC Process Discipline | Example value 1 for Action Approver | 2024-10-15 | 2024-10-15 | DR-PROC-001 Rev B | Open | 2024-09-15 | RT 10 percent random per ASME B31.3 Normal | 2024-09-15 | REF-001 | EPC standard scope, no special notes
Example value 2 for Action ID (Sequential) | Example value 2 for Source Study (HAZOP / HAZID / | REF-003 | 2024-09-20 | Example value 2 for Recommendation Text | Example value 2 for Recommendation Type (Engineeri | Procurement (Vessels) | REF-003 | P&ID-002 Rev B | Example value 2 for Risk Category (Tolerable / ALA | Medium | EPC Mechanical Discipline | Example value 2 for Action Approver | 2024-11-30 | 2024-11-30 | DR-PROC-002 Rev B | In Progress | 2024-09-20 | RT 100 percent per IBR | 2024-09-20 | REF-003 | Brownfield revamp scope, see deviation register

## How to use
How to use the Action Item Tracker Template
This template is for for safety, hazop, and model-review teams.
Step 1: Open the Template tab.
- The first row lists every standard column for this deliverable.
- Example rows below show how to populate each column for typical EPC scope.
Step 2: Replace the example rows with your project data.
- Keep the column headers intact so downstream tools (Excel, Power BI, CAD plug-ins, EDMS bulk loaders) can ingest the structure.
- Add as many rows as your project needs.
Step 3: Validate the populated template before downstream issue.
- Cross-check tag references against P&IDs and equipment list.
- Verify code and standard columns against project applicable codes.
- For India scope, confirm OISD / PESO / CCOE / IBR cross-reference columns are populated where required.
Step 4: If you want this generated automatically from your existing engineering documents, Pathnovo can auto-populate the full template from your P&IDs, datasheets, or source artefacts in 48 hours, with 99.5 percent contractual accuracy on safety-critical fields.
- Workflow detail: https://pathnovo.com/solutions/hazop-safety-intelligence/register-extraction
- Book a demo at https://pathnovo.com/contact
Notes on file format:
- .xlsx native Excel format, compatible with Excel 365, Excel 2019 and later, LibreOffice Calc, Google Sheets import.
- No macros, no embedded scripts, no external links.
- For ERP and EDMS integration, the column structure is designed to map cleanly to SAP PM, IBM Maximo, AVEVA AIM, Cognite Data Fusion, Aconex, Wrench SmartProject.

## About Pathnovo
About Pathnovo
Pathnovo is an engineering document intelligence platform that extracts, reconciles, and delivers structured data from P&IDs, FMEAs, BOMs, datasheets, isometric drawings, HAZOP studies, mill certificates, and other engineering documents into enterprise systems like SAP PM, IBM Maximo, AVEVA AIM, Hexagon SDx, Cognite Data Fusion, and Oracle Aconex.
We deliver this as a managed service with a 99.5 percent contractual accuracy SLA on safety-critical fields and a 48-hour turnaround on initial batches. Used by McDermott (10,247 tags across 600 P&IDs with zero QA rejections at handover) and EPC contractors across India and the GCC region.
Specifically for the Action Item Tracker Template:
- Auto-populated and tracked across reviews.
- Solution detail: https://pathnovo.com/solutions/hazop-safety-intelligence/register-extraction
- Template landing page: https://pathnovo.com/resources/templates/action-item-tracker
Other free engineering templates:
- https://pathnovo.com/resources/templates
Pricing:
- Starter: 1,200 USD per month (1,000 credits)
- Professional: 5,500 USD per month (5,000 credits)
- Scale: from 20,000 USD per month (25,000+ credits)
- 14-day free trial with 100 credits, no credit card
Book a demo:
- https://pathnovo.com/contact
Compliance certifications:
- ISO 9001:2015 (Quality Management System)
- ISO/IEC 27001:2022 (Information Security Management System)
- ISO/IEC 27017 (Cloud Security Controls)
- ISO/IEC 27701 (Privacy Information Management)
Contact:
- hello@pathnovo.com
- +91 75250 46551
- Pathnovo Solutions Private Limited, Bangalore, India