## Template
Deviation ID (Sequential) | Deviation Date | Project / Contract Reference | Discipline (Process / Piping / Mechanical / Electrical / Instrumentation / Civil) | Document / Drawing Reference | Equipment / Tag Reference | Deviation Category (Specification / Code / Client / Vendor / Site) | Deviation Type (Permanent / Temporary / Concession) | Reference Standard or Spec Clause | Required Per Spec | Actual / Proposed | Justification / Technical Basis | Originator (Discipline / Vendor) | Risk Category (Low / Medium / High) | Impact on Safety / Operability / Cost / Schedule | Compensating Measures | Reviewed By (Discipline Lead) | Client / Operator Approver | Approval Status (Pending / Approved / Rejected / Conditional) | Approval Date | Conditions of Approval | Linked NCR or MOC Reference | Closeout Status | Notes
DR-2024-001 (vendor material substitution) | 2024-09-15 | REF-001 | Mechanical (Pumps) | DR-PROC-001 Rev B | REF-001 | ASME B31.3 / ASME Section VIII Div 1 | DR-2024-001 (vendor material substitution) | PMS-A1A Rev C | Example value 1 for Required Per Spec | Example value 1 for Actual / Proposed | Example value 1 for Justification / Technical Basi | Mechanical (Pumps) | Example value 1 for Risk Category (Low / Medium / | Sch 40 | Example value 1 for Compensating Measures | Mechanical (Pumps) | Client Process Manager | Open | EPC Discipline Lead 2024-09-15 | EPC Discipline Lead 2024-09-15 | REF-001 | Open | EPC standard scope, no special notes
DR-2024-002 (vendor code edition) | 2024-09-20 | REF-003 | Procurement (Vessels) | DR-PROC-002 Rev B | REF-003 | API 610 / IEC 60079 | DR-2024-002 (vendor code edition) | PMS-A2A Rev B | Example value 2 for Required Per Spec | Example value 2 for Actual / Proposed | Example value 2 for Justification / Technical Basi | Procurement (Vessels) | Example value 2 for Risk Category (Low / Medium / | Sch 80 | Example value 2 for Compensating Measures | Procurement (Vessels) | Owner Engineering Information Manager | In Progress | Project Engineer 2024-09-20 | Project Engineer 2024-09-20 | REF-003 | In Progress | Brownfield revamp scope, see deviation register

## How to use
How to use the Deviation Register Template
This template is for for qa engineers and project managers.
Step 1: Open the Template tab.
- The first row lists every standard column for this deliverable.
- Example rows below show how to populate each column for typical EPC scope.
Step 2: Replace the example rows with your project data.
- Keep the column headers intact so downstream tools (Excel, Power BI, CAD plug-ins, EDMS bulk loaders) can ingest the structure.
- Add as many rows as your project needs.
Step 3: Validate the populated template before downstream issue.
- Cross-check tag references against P&IDs and equipment list.
- Verify code and standard columns against project applicable codes.
- For India scope, confirm OISD / PESO / CCOE / IBR cross-reference columns are populated where required.
Step 4: If you want this generated automatically from your existing engineering documents, Pathnovo can auto-populate the full template from your P&IDs, datasheets, or source artefacts in 48 hours, with 99.5 percent contractual accuracy on safety-critical fields.
- Workflow detail: https://pathnovo.com/solutions/procurement-intelligence/mdr-automation
- Book a demo at https://pathnovo.com/contact
Notes on file format:
- .xlsx native Excel format, compatible with Excel 365, Excel 2019 and later, LibreOffice Calc, Google Sheets import.
- No macros, no embedded scripts, no external links.
- For ERP and EDMS integration, the column structure is designed to map cleanly to SAP PM, IBM Maximo, AVEVA AIM, Cognite Data Fusion, Aconex, Wrench SmartProject.

## About Pathnovo
About Pathnovo
Pathnovo is an engineering document intelligence platform that extracts, reconciles, and delivers structured data from P&IDs, FMEAs, BOMs, datasheets, isometric drawings, HAZOP studies, mill certificates, and other engineering documents into enterprise systems like SAP PM, IBM Maximo, AVEVA AIM, Hexagon SDx, Cognite Data Fusion, and Oracle Aconex.
We deliver this as a managed service with a 99.5 percent contractual accuracy SLA on safety-critical fields and a 48-hour turnaround on initial batches. Used by McDermott (10,247 tags across 600 P&IDs with zero QA rejections at handover) and EPC contractors across India and the GCC region.
Specifically for the Deviation Register Template:
- Auto-tracked with traceability.
- Solution detail: https://pathnovo.com/solutions/procurement-intelligence/mdr-automation
- Template landing page: https://pathnovo.com/resources/templates/deviation-register
Other free engineering templates:
- https://pathnovo.com/resources/templates
Pricing:
- Starter: 1,200 USD per month (1,000 credits)
- Professional: 5,500 USD per month (5,000 credits)
- Scale: from 20,000 USD per month (25,000+ credits)
- 14-day free trial with 100 credits, no credit card
Book a demo:
- https://pathnovo.com/contact
Compliance certifications:
- ISO 9001:2015 (Quality Management System)
- ISO/IEC 27001:2022 (Information Security Management System)
- ISO/IEC 27017 (Cloud Security Controls)
- ISO/IEC 27701 (Privacy Information Management)
Contact:
- hello@pathnovo.com
- +91 75250 46551
- Pathnovo Solutions Private Limited, Bangalore, India