## Template
Punch ID (Sequential) | Date Raised | Raised By (Name + Organization) | System / Subsystem Reference | Plant / Unit / Area | Equipment / Tag Reference | Drawing / Isometric Reference | Discipline (Civil / Structural / Piping / Mechanical / Electrical / Instrumentation / HVAC / Painting / Insulation) | Punch Category (A / B / C) | Description of Defect or Outstanding Work | Reference Specification or Code Clause | Photo / Evidence Reference | Location (Coordinates / Elevation) | Owner (Subcontractor / Vendor / Discipline Lead) | Target Closeout Date | Closeout Action Taken | Closed By | Closeout Date | Verified By (Commissioning / Client / TPI) | Verification Date | Linked NCR Reference | Notes
Example value 1 for Punch ID (Sequential) | 2024-09-15 | Example value 1 for Raised By (Name + Organization | REF-001 | Unit 100 Crude Pre-Treatment | REF-001 | ISO-10-PA-001 Sheet 14 | Mechanical (Pumps) | Example value 1 for Punch Category (A / B / C) | EPC standard deliverable for Unit 100 scope | PMS-A1A Rev C | REF-001 | Example value 1 for Location (Coordinates / Elevat | Mechanical (Pumps) | 2024-10-15 | Example value 1 for Closeout Action Taken | Example value 1 for Closed By | 2024-09-15 | Client Process Manager | 2024-09-15 | REF-001 | EPC standard scope, no special notes
Example value 2 for Punch ID (Sequential) | 2024-09-20 | Example value 2 for Raised By (Name + Organization | REF-003 | Unit 200 Tank Farm Area A | REF-003 | ISO-6-IA-014 Sheet 22 | Procurement (Vessels) | Example value 2 for Punch Category (A / B / C) | EPC standard deliverable for Unit 200 scope | PMS-A2A Rev B | REF-003 | Example value 2 for Location (Coordinates / Elevat | Procurement (Vessels) | 2024-11-30 | Example value 2 for Closeout Action Taken | Example value 2 for Closed By | 2024-09-20 | Owner Engineering Information Manager | 2024-09-20 | REF-003 | Brownfield revamp scope, see deviation register

## How to use
How to use the Punch List Template
This template is for for commissioning and construction engineers.
Step 1: Open the Template tab.
- The first row lists every standard column for this deliverable.
- Example rows below show how to populate each column for typical EPC scope.
Step 2: Replace the example rows with your project data.
- Keep the column headers intact so downstream tools (Excel, Power BI, CAD plug-ins, EDMS bulk loaders) can ingest the structure.
- Add as many rows as your project needs.
Step 3: Validate the populated template before downstream issue.
- Cross-check tag references against P&IDs and equipment list.
- Verify code and standard columns against project applicable codes.
- For India scope, confirm OISD / PESO / CCOE / IBR cross-reference columns are populated where required.
Step 4: If you want this generated automatically from your existing engineering documents, Pathnovo can auto-populate the full template from your P&IDs, datasheets, or source artefacts in 48 hours, with 99.5 percent contractual accuracy on safety-critical fields.
- Workflow detail: https://pathnovo.com/solutions/engineering-handover
- Book a demo at https://pathnovo.com/contact
Notes on file format:
- .xlsx native Excel format, compatible with Excel 365, Excel 2019 and later, LibreOffice Calc, Google Sheets import.
- No macros, no embedded scripts, no external links.
- For ERP and EDMS integration, the column structure is designed to map cleanly to SAP PM, IBM Maximo, AVEVA AIM, Cognite Data Fusion, Aconex, Wrench SmartProject.

## About Pathnovo
About Pathnovo
Pathnovo is an engineering document intelligence platform that extracts, reconciles, and delivers structured data from P&IDs, FMEAs, BOMs, datasheets, isometric drawings, HAZOP studies, mill certificates, and other engineering documents into enterprise systems like SAP PM, IBM Maximo, AVEVA AIM, Hexagon SDx, Cognite Data Fusion, and Oracle Aconex.
We deliver this as a managed service with a 99.5 percent contractual accuracy SLA on safety-critical fields and a 48-hour turnaround on initial batches. Used by McDermott (10,247 tags across 600 P&IDs with zero QA rejections at handover) and EPC contractors across India and the GCC region.
Specifically for the Punch List Template:
- Auto-classified by Pathnovo from inspection reports.
- Solution detail: https://pathnovo.com/solutions/engineering-handover
- Template landing page: https://pathnovo.com/resources/templates/punch-list
Other free engineering templates:
- https://pathnovo.com/resources/templates
Pricing:
- Starter: 1,200 USD per month (1,000 credits)
- Professional: 5,500 USD per month (5,000 credits)
- Scale: from 20,000 USD per month (25,000+ credits)
- 14-day free trial with 100 credits, no credit card
Book a demo:
- https://pathnovo.com/contact
Compliance certifications:
- ISO 9001:2015 (Quality Management System)
- ISO/IEC 27001:2022 (Information Security Management System)
- ISO/IEC 27017 (Cloud Security Controls)
- ISO/IEC 27701 (Privacy Information Management)
Contact:
- hello@pathnovo.com
- +91 75250 46551
- Pathnovo Solutions Private Limited, Bangalore, India